## Sheet1
PROJECT VARIABLE: | OVERALL: | URBAN: | RURAL: | PROJECT CHALLENGE VARIABLE: | OVERALL: | URBAN: | RURAL: | Project Name: (name, acronym) | Link to report(s): | Donor: | Funding type: (grant, credit) | Total Funding Allocated: (USD - Millions) | Additional (Unplanned) Funding: (USD - Millions) | Percentage funding increase: (unplanned/planned) | Operation Began: (mm/yyyy) | Operartion Ended: (mm/yyyy) | Additonal (unplanned) time required for completion: (months) | Project Status: (closed, active, dropped, pipeline) | Project Location Emphasis: (rural, urban, statewide, n/a) | Project "type": (access, irrigation, medical, edu., etc) | Involvement of Gov't Agency: (agency name) | NGO's in project implementation: (function) | Description of significant problems faced: | Variable - poor Domestic Inst. Capacity: (y/n) | Variable - poor financial management/funding: (y/n) | Variable - poor cooperation /role ambiguity:(y/n) | Variable - procurement /contracting issues: (y/n) | Variable - inadequate planning /standardization: (y/n) | Variable - social/cultural "resist change and vested interest": (y/n) | Project impeded/diverted due to conflict: (y/n) | Involvment of military in project implementation: (y/n) | Plan/Funding in place for project maintenance after completion: (y/n) | Self reported degree of "success": (unsat., mod. Sat., Satasfactory, excellent) | Implementing agency assessment: (unsat., mod. Sat., Satasfactory, excellent) | % of success project dev. Objective indicators "achieved": (percentages, not quantified) | Variable - Aggregate Proj. Dev. Obj. Indicators "achieved" (y/n) | % of success intermediate outcome indicators "achieved": (percentages, not quantified) | Variable - Aggregate Int. Outcome Indicators "achieved" (y/n)
Number projects: | 24 | 11 | 8 | Poor Domestic inst. Capacity: | 83.33% | 81.81% | 75% | EMERGENCY INFRASTRUCTURE RECONSTRUCTION PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2007/04/30/000090341_20070430103810/Rendered/PDF/ICR0000116.pdf | World Bank | credit | 37.11 | 0 | 0% | 2002-06-06 | 2006-06-30 | 18 | closed | urban | infrastructure | Ministry of Urban Development & Housing, Central Authority for Water Supply and Sewerage, Ministry of Energy and Water, Kabul Municipality Ministry of Mines and Industries | NGO consulting, but not implementation | procurement problems at outset, lack of implementing agency capacity, poor understanding of the extent of regional instability | yes | no | no | yes | no | no | no | n/a | yes | satisfactory | moderately satisfactory | no measurement baseline, not quantified | n/a | no measurement baseline, not quantified | n/a
% projects impeded by deteriorating security: | 83.33% | 72.72% | 100% | Poor financial manegement/funding: | 54.16% | 54.54% | 37.5% | EMERGENCY COMMUNITY EMPOWERMENT AND PUBLIC WORKS PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2005/07/29/000012009_20050729094041/Rendered/PDF/331201rev0pdf.pdf | World Bank | grant | 33.7 | 0 | 0% | 2002-06-06 | 2004-12-31 | 0 | Closed | Rural | Rural infrastructure and community empowerment | AFGHANISTAN INTERIM ADMINISTRATION/MINISTRY OF RURAL REHABILITATION & DEVELOPMENT | use of NGO's for provincial implementation | post-conflict regional instability, poor implementing agency capacity | yes | no | no | no | no | no | yes | n/a | no | satisfactory | satisfactory | no measurement baseline, not quantified | n/a | no measurement baseline, not quantified | n/a
% projects Dev. Obj. Indicators "achieved": | 62.5% | 63.63% | 62.5% | Poor Cooperation /Role ambuguity: | 25% | 27.27% | 25% | EMERGENCY EDUCATION REHABILITATION AND DEVELOPMENT PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2007/04/30/000020439_20070430140842/Rendered/PDF/ICR000006.pdf | World Bank | grant | 17.39 | 0 | 0% | 2002-06-06 | 2006-06-30 | 18 | closed | statewide | education | Ministry of Communication, Ministry of Education, Ministry of Higher Education | use of NGO's for provincial implementation | post-conflict regional instability, poor implementing agency capacity, large migrant populations | yes | no | no | no | no | yes | yes | n/a | yes | moderately satisfactory | moderately satisfactory | not quantified | n/a | 84% | no
% projects Mod. Satisfactory and better: | 91.66% | 100% | 81.81% | Procurement /Contracting issues: | 58.33% | 63.63% | 75% | EMERGENCY TRANSPORT REHABILITATION PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2009/02/20/000334955_20090220052635/Rendered/PDF/ICR8900AF0P078101Official0Use0Only1.pdf | World Bank | credit and supplemental grant | 106.9 | 26.9 | 25.16% | 2003-03-11 | 2008-06-30 | 28 | closed | urban | transportation | Ministry of Public Works Ministry of Transport and Civil Aviation | n/a | regional instability, mine affected areas, poor financial management, inadequate sustainability measures, lack of institutional capacity | yes | yes | no | no | no | no | yes | n/a | no | moderately satisfactory | moderately satisfactory | success | yes | success | yes
Project received term augment: | 87.5% | 100% | 75% | Inadequate planning /standardization: | 41.66% | 54.54% | 50% | NATIONAL EMERGENCY EMPLOYMENT PROGRAM PHASE I (NEEP I) | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2010/01/29/000333037_20100129003040/Rendered/PDF/ICR12200P091031C0disclosed011271101.pdf | World Bank | grant | 52.8 | 36.2 | 68.56% | 2003-03-14 | 2009-03-31 | 54 | closed | rural | rural access | Ministry of Irrigation, Water Resources and Energy Ministry of Public Works Ministry of Public Works United Nations Office for Project Services (UNOPS) | n/a | regional instability, competition with opiate trade, inadequate sustainability measures, lack of institutional capacity | yes | no | no | no | no | yes | yes | n/a | no | satisfactory | satisfactory | no measurement baseline, not quantified | n/a | no measurement baseline, not quantified | n/a
Received funding augment: | 54.16% | 36.36% | 87.5% | Social/cultural resistsance to proj. goals: | 29.16% | 27.27% | 25% | HEALTH SECTOR EMERGENCY RECONSTRUCTION AND DEVELOPMENT PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2010/06/30/000333037_20100630031347/Rendered/PDF/ICR12940P078321C0disclosed061281101.pdf | World Bank | grant | 76.5 | 32.8 | 42.88% | 2003-06-05 | 2009-06-30 | 26 | closed | statewide | health sector | Ministry of Public Health | use of NGO's for implementation | Procurement problems, lack of implementing agency capacity, insufficient project funding, ambiguity in cooperative responsibilities | yes | yes | yes | yes | no | no | no | n/a | no | satisfactory | highly satasfactory | 187%, 87%, 105%, 76%, 71%, 99%, 104%, 100%, and some with no baseline | yes | 86%, 57%, 94%, 158%, 88%, 131%, 139%, and some with no baseline | yes
Mean ratio of funding increase to overall disbursement: | 18.93% | 9.938% | 35.52% | Proj. impeded/diverted due to conflict: | 83.33% | 72.72% | 100% | NATIONAL EMERGENCY EMPLOYMENT PROGRAM FOR RURAL ACCESS (NEEPRA) | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2008/08/05/000333038_20080805040153/Rendered/PDF/ICR00006250ICR1Disclosed0Aug0102008.pdf | World Bank | credit, grant | 41.61 | 13.31 | 31.99% | 2003-06-24 | 2007-09-30 | 12 | closed | rural | rural access | Ministry of Public Works, Ministry of Rural Rehabilitation & Development | NGO's with double identities as contracting firm encroached on implementation | severe regional instability, lack of implementing agency capacity, weak domestic contracting sector | yes | no | no | yes | no | no | yes | n/a | no | satisfactory | moderately satisfactory | 108%, 234%, 123%, 100%, 100% | yes | N/A | n/a
Explicit Military involvement: | 3 | 2 | 0 |  |  |  |  | EMERGENCY COMMUNICATIONS DEVELOPMENT PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2010/12/15/000356161_20101215041809/Rendered/PDF/ICR13260P083721e0only1910BOX353800B.pdf | World Bank | credit | 22 | 0 | 0% | 2003-10-07 | 2009-09-30 | 24 | closed | statewide | telecommunications | Ministry of Communications and Information Technology, Afghanistan Telecommunications Regulatory Authority, Afghan Post | n/a | lack of domestic institution project management capacity, deteriorating security slowed implementation and impeded consultant travel | yes | yes | no | no | no | no | yes | n/a | no, proposed telecom privitization | highly satisfactory | satisfactory | 133%, 100%, 100%, 100%, 100%, 100%, | yes | 100% | yes
Plan/funding for proj. maintenance: | 45.83% | 45.45% | 37.5% |  |  |  |  | Improvement of Power Supply to Kabul Project | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2009/10/21/000334955_20091021032007/Rendered/PDF/ICR11430P0910610disclosed0101191091.pdf | World Bank | grant | 7.4 | 0 | 0% | 2003-12-10 | 2009-03-31 | 30 | closed | urban | power supply | Ministry of Energy and Water (MEW) | n/a | insufficient funding and logistical planning at outset, area security concerns failed to diminish as expected, seasonal and contracting limitations | no | yes | no | yes | yes | no | yes | n/a | no | moderately satisfactory | moderately satisfactory | target exceeded | yes | target exceeded | yes
Implementing agency rating Mod. Satisfactory of better: | 51.66% | 63.63% | 100% |  |  |  |  | EMERGENCY NATIONAL SOLIDARITY PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2008/07/08/000333038_20080708021028/Rendered/PDF/ICR5240REVISED1isclosed0July0202008.pdf | World Bank | grant | 166.3 | 71.3 | 42.87% | 2003-12-23 | 2007-03-31 | 0 | closed | Rural | community infrastructure | Ministry of Rural Reconstruction & Development | implementation partnership with ngo's | high rural security risks culminating in 2006, lack of engineering capacity, inadequate initial funding, delays in budget coordination and funding transfer, emphasis on project expansion rather than consolidation and completion | yes | yes | yes | yes | yes | no | yes | n/a | yes | satisfactory | satisfactory | 124%, 126%, targets met (but female participation measurement is questionable) | yes | 250%, 138% | yes
NGO's as implementing partners: | 41.66% | [6 empty] | EMERGENCY IRRIGATION REHABILITATION PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2013/07/01/000445729_20130701124006/Rendered/PDF/ICR21980P078930C0disclosed060270130.pdf | World Bank | credit and supplemental grants | 126.5 | 86.5 | 68.38% | 2003-12-23 | 2011-12-31 | 51 | closed | Rural | irrigation infrastructure | Ministry of Energy and Water | n/a | deteriorating security situation mid-project, lack of capacity via qualified staff in implementing agency, civil works procurment delays, inconsistent capacity building for implementing agencies, | yes | no | no | yes | yes | no | yes | n/a | yes | satisfactory | moderately satisfactory | 54%, no measurement baseline, not quantified | no | no measurement baseline, not quantified | n/a
[8 empty] | EMERGENCY CUSTOMS MODERNIZATION AND TRADE FACILITATION PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2011/09/02/000356161_20110902014516/Rendered/PDF/ICR15360P083900e0only0900BOX361536B.pdf | World Bank | credit and supplemental grant | 37.8 | 6.8 | 17.99% | 2003-12-23 | 2010-12-31 | 36 | closed | statewide | customs infrastructure | Department of Customs, Ministry of Finance | n/a | poor implementing agency capacity and organization, heavy reliance on UNOPS as IP, 2006 security deterioration, domestic agency reform was slow | yes | yes | no | no | no | no | yes | yes | yes | highly satisfactory | satisfactory | 5/9 indicators exceeded, 2/9 lack baseline measure, 2/9 not met | yes | no measurement baseline, not quantified | n/a
[8 empty] | EMERGENCY POWER REHABILITATION PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2013/10/21/000356161_20131021111603/Rendered/PDF/ICR04350ICR0Af000PUBLIC00Box379845B.pdf | World Bank | credit and supplemental grant | 110.24 | 5.24 | 4.753% | 2004-06-22 | 2013-03-31 | 50 | closed | urban | power supply | Ministry of Energy and Water | n/a | incomplete technical designs, procurement delays, political uncertainty, poor security and transportation, "resistance to change and vested interest", lack of domestic institution capacity, lack of contracting market | yes | no | no | yes | yes | yes | yes | yes | yes | moderately satisfactory | moderately unsatisfactory | 256% of target | yes | 75%, 100%, 100%, "achieved with some delay" | yes
[8 empty] | EDUCATION QUALITY IMPROVEMENT PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2009/10/16/000350881_20091016095920/Rendered/PDF/ICR12630P0839610disclosed0101151091.pdf | World Bank | grant | 35 | 0 | 0% | 2004-07-29 | 2009-03-31 | 0 | closed | statewide | education | Ministry of Education | implementation partnership with ngo's | cultural constraints with female population in the teaching workforce, initial lack of feduciary management led to cost constraints, security concerns limited personell travel and made quality control assessment difficult | yes | yes | no | no | no | yes | yes | n/a | yes | moderately satisfactory | n/a | unsatasfactory, 89%, no measurement baseline X3, not completed | no | lack of adequate measurement, targets not achieved | no
[8 empty] | KABUL URBAN RECONSTRUCTION PROJECT (KURP) | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2013/03/15/000333037_20130315122226/Rendered/PDF/ICR22420P083910C0disclosed030130130.pdf | World Bank | grants | 33.8 | 0 | 0% | 2004-07-29 | 2012-04-30 | 37 | closed | urban | services and facilities infrastrucure | Ministry of Urban Development Affairs (MoUDA) | n/a | overly ambitious project design, societal dispute over Kabul's dev. (desire to remain unchanged), implementing agency poor capacity and frequent personell turnover, limited construction industry, lack procurment conformity to Bank policy, security delays and oil price increase | yes | no | yes | yes | yes | yes | yes | n/a | yes | moderately satisfactory | satisfactory | achieved | yes | target achieved X3, target indicator dropped | yes
[8 empty] | AFGHANISTAN SHORT TERM URBAN WATER SUPPLY AND SANITATION PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2011/12/15/000356161_20111215232914/Rendered/PDF/ICR18460P0921600disclosed0120140110.pdf | World Bank | grant | 41 | 21 | 51.22% | 2005-02-18 | 2010-12-31 | 36 | closed | urban | water supply and sanitation | MoUD - Ministry of Urban Development | n/a | ambitious geograohical scope and inappropriate planning, security limitations to project management and travel, insufficient funding and payment delays from Bank, poor agency cooperation and role ambiguity, limited contracting and contruction materails delivery delays | yes | yes | yes | yes | yes | no | yes | yes | no, attempting to transfer project responsibility to PRT's | unsatisfactory | moderately unsatisfactory | non completion of works and no measurement | no | non completion of works and no measurement X4 | no
[8 empty] | STRENGTHENING HIGHER EDUCATION PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2014/01/09/000461832_20140109125718/Rendered/PDF/ICR28590P089040IC0disclosed01070140.pdf | World Bank | grants | 55.7 | 15.7 | 28.19% | 2005-05-19 | 2013-06-30 | 36 | closed | urban | university education | Ministry of Higher Education | n/a | Constant reforms in the Afgh administrative apparatus, lack of bureaucratic effeciency as a result of poor fiscal autonomy, changes in iniversity personell, lack of project plan coherence, reluctance of international university partnerships, security limitations | yes | no | no | no | yes | no | yes | n/a | no | satisfactory | moderately satisfactory | 100%, 99%, 110%, achieved X4 | yes | 100%, 75%, 100% X4 | yes
[8 empty] | RURAL WATER SUPPLY AND SANITATION PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2010/08/10/000333038_20100810035920/Rendered/PDF/ICR13650P091031Official0Use0Only191.pdf | ARTF | grant | 6.2 | 1.2 | 19.35% | 2005-12-15 | 2009-12-31 | 30 | closed | Rural | water supply and sanitation | Ministry of Rural Rehabilitaton and Development (MRRD) | Project targets NGO's for capacity building in outcome implementation | deteriorating security situation impeded project site visitation, unavailability of willing project management, planning and implementation arrangement changes mid-project, procurement issues and payment delays | no | yes | no | yes | yes | no | yes | n/a | no | moderately satisfactory | moderately satisfactory | no measurement baseline, but general reported success | yes | n/a | n/a
[8 empty] | AFGHANISTAN URBAN WATER SECTOR PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2014/12/31/000442464_20141231094014/Rendered/PDF/ICR30500P0878600disclosed0120290140.pdf | World Bank | grant | 17.83 | 0 | 0% | 2006-05-25 | 2014-06-30 | 48 | closed | urban | water supply and sanitation | Afghanistan Urban and Water Supply and Sanitation Components | n/a | delays resulting from security deterioration in 2013, delays in management and recruitment, disbursement delays | no | yes | no | no | no | no | yes | n/a | no | moderately satisfactory | moderately satisfactory | no measurement baseline | n/a | no measurement baseline, dropped due to delays | no
[8 empty] | KABUL, AYBAK, MAZAR-E-SHARIF POWER PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2013/10/21/000442464_20131021111133/Rendered/PDF/ICR29010ICR0Af000PUBLIC00Box379845B.pdf | World Bank | grant | 49.9 | 0 | 0% | 2007-10-04 | 2013-03-31 | 39 | closed | urban | power supply | Ministry of Energy and Water | n/a | security deterioration between 2008 and 2013, "resistance to change and vested interest", transportation and climate limitations, weak insitutional capacity and poor coordination, limited goods and contractors, changes in design and resulting cost overruns | yes | no | yes | yes | yes | yes | yes | n/a | no | unsatisfactory | moderately unsatisfactory | 253%, achieved, 174% | yes | 100% X3 | yes
[8 empty] | NATIONAL EMERGENCY RURAL ACCESS PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2014/07/25/000333037_20140725111523/Rendered/PDF/ICR30210ICR0P1033430Box0385290B00PUBLIC0.pdf | World Bank | grants | 228.65 | 91.65 | 40.08% | 2007-12-13 | 2013-12-31 | 36 | closed | Rural | rural access | Ministry of Public Works, Ministry of Rural Rehabiliation and Development (MRRD) | yes (but unclear role) | no standardized project output design led to "overengineering" and cost overruns, deteriorationg security led to delays and cost overruns, poor domestic insitutional capacity: poor compliance and feduciary management norms MRRD, poor safeguard managing and staffing MPW | yes | yes | no | yes | yes | no | yes | n/a | no | moderately satisfactory | moderately satisfactory | 100%, target exceeded X3, indicator dropped | yes | target exceeded X5, achieved X4, partially achieved X4, not achieved X4 | yes
[8 empty] | AFGHANISTAN SKILLS DEVELOPMENT PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2015/01/06/000477144_20150106123805/Rendered/PDF/ICR32520P102570IC0disclosed01050150.pdf | World Bank | grants | 34.01 | 0 | 0% | 2008-01-31 | 2014-06-30 | 16 | closed | urban | education | Ministry of Education (MoE), Deputy Ministry of Technical and Vocational Education and Training (DMTVET), National Skills Development Program (NSDP), Ministry of Labor and Social Affairs, Martyrs and Disabled (MoLSAMD), and the Committee on Education and Skills Policy (CESP) | n/a | High turnover in the leadership of the implementing ministries and agencies, Lack of Government action on granting financial autonomy to public insitutes (project targets), security situation made it difficult to attract and retain good international consultants and academic staff | yes | yes | no | no | no | no | no | n/a | yes | moderately satisfactory | moderately satisfactory | achieved X2, exceeded X2, partially achieved | yes | achieved X5, exceeded X4, partially achieved | yes
[8 empty] | KABUL URBAN ROADS IMPROVEMENT PROJECT | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2012/07/19/000356161_20120719005831/Rendered/PDF/ICR23250P107100C0disclosed070170120.pdf | World Bank | grant | 16.14 | 0 | 0% | 2008-12-19 | 2011-12-31 | 12 | closed | urban | urban roadways | Kabul Municipality | n/a | KM failed to attract candidates to staff the Project Management Unit, difficulty accessing construction sites in heavily trafficked areas, poor domestic agency capacity: poor contracting management, cash flow issues | yes | yes | no | yes | no | no | no | n/a | yes | satisfactory | moderately unsatisfactory | no measurement baseline, not quantified | n/a | no measurement baseline, not quantified | n/a
[8 empty] | STRENGTHENING HEALTH ACTIVITIES FOR THE RURAL POOR (SHARP) | http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2014/04/16/000442464_20140416095040/Rendered/PDF/ICR29750P112440C0disclosed040140140.pdf | World Bank | grants | 144.63 | 18.63 | 12.88% | 2009-03-24 | 2013-09-30 | 6 | closed | Rural | medical infrastructure | Ministry of Public Health | NGO's used for project implementation | deteriorating security hampered monitoring, impeded medicine dist., and disincentivised women from participating, Problems coorinating and contracting NGO's, General problems recruiting training and retaining female staff in rural regions | no | no | yes | yes | no | yes | yes | n/a | yes | satisfactory | moderately satisfactory | 97.5%, 100%, 118%, 78%, 169%, 108%, no measurement baseline | yes | 114%, "modest progress" - no measurement, 185%, no measurement baseline X3, achieved | yes